## Instructions
Association of Caribbean States
Request for Information ¦ Records Management Solution
Digitisation RFP 2022 ¦ Statement of Work(SOW)
Instructions
There are seven (7) worksheets in this Excel Workbook which you are requested to complete and submit as part of your response.
Please select each worksheet and provide a response to each statement/question provided.
If you have additional information to provide under each of the headings, you are free to add this below each list.
Bidders must select a response to each responsibility requirement in each worksheet under the column Bidder Response
Failure to provide a “Yes” or applicable response without providing a comment as to why the requirement cannot be met and an alternative approach may cause the Proposal to be rejected
A “Yes” response signifies agreement with the details of the task deliverable
A “No” response signifies disagreement with the details of the task deliverable
A “Not Available” response signifies a specific incapability or incapacity regarding a task deliverable
A “To Be Confirmed” response signifies a need to determine acceptance/non acceptance regarding a task deliverable subject to other terms/conditions unknown or undisclosed.
Project Roles and Responsibilities Key Terms
LEAD | - Entity will initiate effort.
RESPONSIBLE | - Entity must complete the task or objective or make the decision.
ACCOUNTABLE | - Entity must sign off or approve when the task, objective or decision is complete.
CONSULTED | - Entity will provide guidance or give input before the task work can be done, during the effort and/or before completion.
INFORMED | - Entity will be provided updates on progress or decisions approved.
SUPPORT | - Entity will provide general assistance to other entities or stakeholders.

## ProjectManage
Project Management
|  | Project Roles and Responsibilities |  | BIDDER SUBMISSIONS
Deliverable Task ID Number | Task or Deliverable Description | ACS-AEC | Bidder | Bidder Response | Bidder Comments
1 | Provide a Project Manager (PM) to represent the Bidder in the management of the project, interfacing with the ACS in any decisions relating to the project. | SUPPORT | LEAD RESPONSIBLE
2 | Provide a robust project management methodology and toolkit founded on industry best practices. | SUPPORT | LEAD RESPONSIBLE
3 | Conduct project management activities throughout the lifecycle and execute the associated plans. | SUPPORT | LEAD RESPONSIBLE
4 | Establish a formal requirements management process that shall include: • Assumption Definition, Tracking, and Traceability • Business and Technical Requirement Definition, Tracking, Traceability and Verification • Operational Change Process • Phase and Product Entry and Exit (Acceptance) Criteria Definition, Tracking and Signoff | SUPPORT | LEAD RESPONSIBLE
5 | Provide a Project Charter which outlines the scope, timeline, objectives, organization structure, project approach, high-level deliverables, resources, and governance structure. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
6 | Provide a Project Operational Change Plan that defines roles, responsibilities for establishing procedures and managing Operational Change requests. | SUPPORT | LEAD RESPONSIBLE
7 | Provide, update, and maintain throughout the lifecycle of the project a Project Schedule which includes, but is not limited to the following components: • Tasks • Activities • Milestones • Resources • Dependencies • Task and activity durations • Critical path identification | SUPPORT | LEAD RESPONSIBLE
8 | Project Management Plan: Provide, update, and maintain a formal Project Management Plan (PMP) that includes the following key components: • Project initiation activities • Critical path identification, and dependencies • Issue tracking, escalation, and resolution • Operational change request approval and tracking • Schedule/milestone tracking and resource allocation • Budget management, expenditure control, and project earned value as mutually agreed upon by the ACS and Bidder • Deliverable/product review and approval and other acceptance criteria • Bidder and subcontractor management • Project success evaluation criteria and project close-out activities • Relationships to other IT or business efforts • Status and other reporting activities | SUPPORT | LEAD RESPONSIBLE
9 | Risk Management Plan: Provide a Risk Management Plan that shall be used, quantify the potential impact of each identified risk, present mitigation plans for each identified risk, and enact appropriate risk responses. | SUPPORT | LEAD RESPONSIBLE
10 | Implement risk mitigation measures and contingency plans as high-priority risks are identified and monitored. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
11 | Provide an Issue Management and Resolution Strategy and process including identification, tracking, and resolution of issues. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
12 | Training and Knowledge Transfer Strategy and Plan: Provide formal Training and Knowledge Transfer Strategy and Plans to document training requirements and the approach the ACS will use for updating training requirements, development of training curricula, and deploying training for the ACS staff as required. Include specific knowledge transfer milestones with clear deliverables for each set of activities | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
13 | Master Test Strategy: Provide a Master Test Strategy that describes the approach that will be taken to fully test all components of the system including test control and approval processes, test participants, how testing will interface with the configuration management process, and test documentation expectations for the following test types: unit, functional, volume, end-to-end, document conversion/migration validation, security, integration, response time & capacity, regression, and user-acceptance. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
14 | Provide formal Communication Strategy and Plans that shall be used to communicate with all project stakeholders throughout the life of the project including, at a minimum, the following activities: • Communication with internal and external stakeholders • Formal kickoffs of phases • Communication of milestones • Status reports | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
15 | Provide a Quality Management Plan that designates a Quality Management Planning Team (made up of Bidder and ACS officials and a liaison to work with ACS officials to resolve any emerging problems or areas of concern and to ensure standards are being met. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
16 | Project Status Reports: Provide Project Status Reports and conduct regularly scheduled status meetings reviewing project progress, planned activities, major milestones and project deliverables, all critical path dependencies and bottlenecks, staffing resources, risk management, issues/issue resolution and next steps. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
17 | Provide a toolset to support project activities such as issues management, requirements management, and change management, etc., accessible by all internal and external project team members | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
18 | Ensure alignment of the system with the technical architecture, security guidelines and IT policies and procedures of the ACS. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
19 | Prepare and track ACS change requests and document impact analysis associated with proposed changes. | LEAD | LEAD RESPONSIBLE
20 | Approve and prioritize changes. | RESPONSIBLE ACCOUNTABLE | SUPPORT RESPONSIBLE
21 | Provide all training necessary to ensure that Bidder project team members are appropriately skilled and knowledgeable on all industry-standard and related best practice components utilized in establishing the RMS test environments and the supporting platform. This also includes best practices on business processes and configuration of RMS to meet ACS operational equirements | RESPONSIBLE ACCOUNTABLE | LEAD RESPONSIBLE
22 | Document deliverable details, formats, and acceptance criteria in Deliverable Expectation Documents (DED). | RESPONSIBLE ACCOUNTABLE | LEAD RESPONSIBLE
23 | Approve DED. | RESPONSIBLE ACCOUNTABLE | SUPPORT RESPONSIBLE

## SoftwareService
Software Solution Configuration & Management
|  | Project Roles and Responsibilities |  | BIDDER SUBMISSIONS
Deliverable Task ID Number | Task or Deliverable Description | ACS-AEC | Bidder | Bidder Response | Bidder Comments
1 | Software Configuration Management Policies and Procedures: Create documentation that specifies package configuration decisions according to the consensus business rules developed during requirements definition. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
2 | Provide a System Landscape, Technical, and Design Document which outlines the high-level system architecture to be used throughout all phases of the project, the technical and business integration with other ACS applications or information systems | SUPPORT | LEAD RESPONSIBLE
3 | Functional and Technical Requirements: Provide detailed functional and technical requirements including requirements documents, use cases, workflow, and logical diagrams. | SUPPORT | LEAD RESPONSIBLE
4 | Provide Detailed Design Standards and Design Documents, including configuration settings, based on the detailed functional and technical requirements. | SUPPORT | LEAD RESPONSIBLE
5 | Facilitate interviews, group workshops, etc to obtain and gain consensus on any design approaches | SUPPORT | LEAD RESPONSIBLE
6 | Document/create the Technical System Design Document specifying all components, modules, data stores, reports, interfaces, interface components, Bidder-Proposed Enterprise Technology Tools, and associated operations procedures for the system. | SUPPORT | LEAD RESPONSIBLE
7 | Review and approve detailed design documentation. | ACCOUNTABLE | RESPONSIBLE
8 | Approve standards and methodologies. | ACCOUNTABLE | RESPONSIBLE
9 | Perform all necessary technical design, development, configuration, document conversion/migration, unit testing, and scripting, of system modules as required to provide and implement the design specifications. | SUPPORT | LEAD RESPONSIBLE
10 | Provide and document performance-enhancement adjustments to system software and utilities. | SUPPORT | LEAD RESPONSIBLE
11 | Manage all configuration and interface development efforts using industry-standard project management tools and methodologies | SUPPORT | LEAD RESPONSIBLE
12 | Review and approve results of Bidder release candidate reviews at the discretion of ACS Secretary General. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE

## BPR
Process & Digitisation
|  | Project Roles and Responsibilities |  | BIDDER SUBMISSIONS
Deliverable Task ID Number | Task or Deliverable Description | ACS-AEC | Bidder | Bidder Response | Bidder Comments
1 | Document functional and technical planning sessions. | SUPPORT | LEAD RESPONSIBLE
2 | Conduct and document value assessments of Detailed Functional and Technical Requirements (including requirements documents, security, workflow, use cases, and logical diagrams). | SUPPORT | LEAD RESPONSIBLE
3 | Business Process Fit/Gap Analysis: Generate a Business Process Fit/Gap Analysis, including affected systems recommendations and alternative design scenarios, etc. | SUPPORT | LEAD RESPONSIBLE
4 | Provide a Business Solution that shall define the overall design for the implementation of the ACS DMS projects, including at a minimum: • Business and architectural end-state design for the RMS system • Integration points between the Project to consider in the design and configuration • Accounting and organizational hierarchy elements for the integration and maintenance of the application • Reporting strategy | SUPPORT | LEAD RESPONSIBLE
5 | Conduct and document interviews, group workshops, and surveys to define, gather, refine, and prioritize detailed functional and technical requirements. | SUPPORT | LEAD RESPONSIBLE
6 | Create/provide documentation that specifies all components, system modules, document flows, interface components and associated operations procedures for the RMS test environment. | SUPPORT | LEAD RESPONSIBLE
7 | Functional and Technical Requirements: Provide detailed functional and technical requirements including requirements documents, use cases, workflow, and logical diagrams. | SUPPORT | LEAD RESPONSIBLE
8 | Provide Detailed Design Standards and Design Documents, including configuration settings, based on the detailed functional and technical requirements. | SUPPORT | LEAD RESPONSIBLE
9 | Provide Draft and Final Business Solutions Documents for components and re-engineered business process. | SUPPORT | LEAD RESPONSIBLE
10 | Provide and document a Business Process and Organizational Change Management Plan. | SUPPORT | LEAD RESPONSIBLE
11 | Configuration of package-based parameters and codes tables to provide specific business rules, workflows, and information exchange and interpretation using the functionality of the RMS modules. | SUPPORT | LEAD RESPONSIBLE

## Testing
Technical and End User Testing
|  | Project Roles and Responsibilities |  | BIDDER SUBMISSIONS
Deliverable Task ID Number | Task or Deliverable Description | ACS-AEC | Bidder | Bidder Response | Bidder Comments
1 | End to End Test Plans: Create/document Unit, Integration, End-to-End, User Acceptance, Document Conversion, Regression, and Security Test Plans. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
2 | Create test environments necessary to support the ongoing application development/configuration including any elements required for supporting the enhanced functions or features. | SUPPORT | LEAD RESPONSIBLE
3 | Install Bidder-Proposed Enterprise Technology Tools (and any other utilities/tools if required to support the Bidder's methodology) in the test environments necessary to support the ongoing application development/configuration including any elements required for supporting any enhanced functions or features. | SUPPORT | LEAD RESPONSIBLE
4 | Document/create standards, policies, procedures, and tools for all integration and testing activities. | SUPPORT | LEAD RESPONSIBLE
5 | Document/create RMS data/document and information management standards, methodologies, and tools to support integration and testing activities. | SUPPORT | LEAD RESPONSIBLE
6 | Final Test Plans and Test Scripts: Provide all Test Plans and Test Scripts in alignment with the Master Test Strategy. | SUPPORT | LEAD RESPONSIBLE
7 | Establish formal Response Time and Capacity Testing Strategy and Plans. | SUPPORT | LEAD RESPONSIBLE
8 | Provide and recommend Configuration and Technical Documentation Policies, procedures, and standards in conformance with Software Engineering Institute (SEI) requirements where applicable. | SUPPORT | LEAD RESPONSIBLE
9 | Establish, document, remediate, and maintain the overall Reports, Interfaces, Conversions, Enhancements and Workflows, Development Schedule. | SUPPORT | LEAD RESPONSIBLE
10 | Test Cases and Test Data: Create Test Cases and Test Data that are fully documented and repeatable without consulting assistance. | SUPPORT | LEAD RESPONSIBLE
11 | Conduct all appropriate testing (e.g. unit testing, end-to-end testing, response time and capacity testing, regression testing, parallel testing). | SUPPORT | LEAD RESPONSIBLE
12 | Test Results Documentation: Provide and document test results, Documented Successful Testing Results. | SUPPORT | LEAD RESPONSIBLE
13 | Validate the system for compliance with the System Security Strategy and Plans. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
14 | Review testing results for compliance with policies, procedures, plans, and test criteria and metrics (e.g. defect rates, progress against schedule). | SUPPORT | LEAD RESPONSIBLE
15 | Coordinate user acceptance testing (e.g. gain user involvement, establish and define acceptance criteria, setting high-level test objectives, establish high-level test scenarios, establish end-to-end test scenarios). | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
16 | User Acceptance Testing: Facilitate and support user acceptance testing as prescribed by the ACS, including: establishing adequate test environment based on user acceptance criteria; preparing data to support test scenarios within modified system as well as managing the relationship with all interfaced systems necessary to conduct test; troubleshooting; supporting users to progress through scenarios; simulating interfaces or working with integrated systems to conduct end-to-end tests; supporting document batch/load processing; exercising functionality; and reporting results. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
17 | Conduct and complete user acceptance test plan | ACCOUNTABLE | SUPPORT
18 | The Bidder shall recommend, and upon approval, support the ACS in implementing a shared access to a Defect Tracking System (provided by the Bidder) for purposes of allowing the ACS to initiate, track, and report ACS found defects (i.e., user acceptance testing). | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
19 | Notify Bidder in the event the ACS notices a discrepancy between the ACS's requirements and the requirements document or other Bidder deliverables | LEAD RESPONSIBLE | SUPPORT
20 | Correct defects found as a result of testing efforts. | SUPPORT | RESPONSIBLE

## Staging
Technical Staging/Demonstration
|  | Project Roles and Responsibilities |  | BIDDER SUBMISSIONS
Deliverable Task ID Number | Task or Deliverable Description | ACS-AEC | Bidder | Bidder Response | Bidder Comments
1 | Staging/Migration Plans: Configure automated document conversion/migration uploads into the RMS using best practices tools and techniques that are consistent with | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
2 | Coordinating and executing manual document uploads if required. | ACCOUNTABLE | LEAD RESPONSIBLE
3 | Deployment Plans: Provide Initial and Final Deployment Plans (turn-over-to-production plan). | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
4 | Conduct pre-installation business surveys to assess site readiness against a set of best practices checklist criteria. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
5 | Develop Site-specific Transition Plans that encompass business process, operations (business and IT), and technology support plans that need to be in place to mitigate implementation risk. Coordinate this documentation with site-specific end-user training activities. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
6 | Site Training Documentation: Deliver Site-specific training and associated System and User Documentation, including Business Process and Procedures (BPPs) and any changes to policies or procedures. Coordinate with site-specific end-user training activities. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
7 | Provide Recommended Operations and Administration Procedures related to the deployment. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
8 | Provide Role to Position Mapping Document which outlines the security roles, positions, and authorizations configured in the system. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
9 | Track deployment and document migration/conversion status and notification. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
10 | Provide a Post Production Support Strategy which outlines the processes for end-users to obtain support in the post go-live environment. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
11 | Provide formal Business Continuity Strategy and Plans that describes the approach that will be taken to adhere to SLRs and perform business disaster recovery activities. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
12 | Provide a Business Contingency Plan that describes the approach that will be taken during go-live activities. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
13 | Batch Job Schedule: Provide Batch Schedule which sequences the execution of automated background jobs for processing with other ACS production jobs or activities. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
14 | Provide metrics regarding scalable and acceptable levels of performance. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
15 | Develop Level 2 and 3 help desk scripts. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
16 | Create Go/No-go Checklist. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
17 | Approve production deployment go/no-go decisions. | ACCOUNTABLE | SUPPORT
18 | Conduct Go/No-go Meeting and develop Go/No-go Documentation. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE
19 | Provide metrics regarding scalable and acceptable levels of performance. | ACCOUNTABLE SUPPORT | LEAD RESPONSIBLE

## Training
Technical & Operational Training
|  | Project Roles and Responsibilities |  | BIDDER SUBMISSIONS
Deliverable Task ID Number | Task or Deliverable Description | ACS-AEC | Bidder | Bidder Response | Bidder Comments
1 | Provide training materials for initial training and knowledge transfer to the ACS. | SUPPORT | LEAD RESPONSIBLE
2 | Initial Training and Knowledge Transfer: Provide initial training and knowledge transfer to the support organization, in accordance with the Training and Knowledge Transfer Plan, to support the detailed requirements definition phase of implementation activities. | ACCOUNTABLE | LEAD RESPONSIBLE
3 | Provide a Training Curriculum Document which outlines the training and course content including the course topics and the content to be delivered with each topic. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
4 | Provide formal End-user Training Strategy and Plans to document training requirements and the approach the ACS will use for updating training requirements, development of training curricula, and deploying training for the end-users as required. Include training milestones with clear deliverables for each set of activities. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
5 | Perform Organizational Readiness Assessment to identify opportunities and resistance to changes. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
6 | Provide initial End-user Training for the system. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
7 | Provide training materials, including dialogue scripts, for Level 2 support for the system to the ACS and other vendor personnel as applicable. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
8 | Organization Change Management Recommendation: Provide recommendations for ongoing business process and organizational change management activities | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE

## PostDeploy
Production Deployment & Post Implementation
|  | Project Roles and Responsibilities |  | BIDDER SUBMISSIONS
Deliverable Task ID Number | Task or Deliverable Description | ACS-AEC | Bidder | Bidder Response | Bidder Comments
1 | Provide monthly reports detailing the warranty work (i.e., number and type of defects, status of defects). | SUPPORT | LEAD RESPONSIBLE
2 | Perform system fixes to correct system-level performance problems that the Bidder was responsible for. | ACCOUNTABLE | LEAD RESPONSIBLE
3 | Perform fixes to correct translation or load errors for interfaces that the Bidder was responsible for. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
4 | Perform fixes to correct improperly converted files or tables that the Bidder was responsible for. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
5 | Perform fixes to correct errors from application configuration or parameter table settings that are not consistent with the intended design and were the responsibility of the Bidder. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
6 | Perform training fixes to correct interpretation and documentation errors related to user or technical training documentation or other training delivery media developed by the Bidder | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
7 | Test the system to ensure that no regression errors are introduced. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
8 | Approve of all Warranty Service fixes with formal sign-off. | ACCOUNTABLE | SUPPORT
9 | Conduct performance monitoring | RESPONSIBLE ACCOUNTABLE | SUPPORT
10 | Perform system administration, if required. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
11 | Perform software configuration, if required. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
12 | Perform software customization, if required. | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
13 | Perform report development (as requested per approved change order). | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
14 | Execute and maintain the Business Contingency Plan. | RESPONSIBLE | SUPPORT
15 | Conduct ongoing end-user training. | LEAD RESPONSIBLE | SUPPORT
16 | Maintain “End State” system architecture. | LEAD RESPONSIBLE | SUPPORT
17 | Document/create Maintenance and Repair Policies and Procedures | LEAD RESPONSIBLE | SUPPORT
18 | Document/create a System Maintenance Plan (e.g. committed and proposed work schedules if applicable). | LEAD RESPONSIBLE | SUPPORT
19 | Provide system maintenance plan for all categories of maintenance services (e.g. Minor Enhancements, Corrective Maintenance, Preventative Maintenance, Adaptive Maintenance, and Perfective Maintenance) | SUPPORT | LEAD RESPONSIBLE
20 | Provide technical and functional support to the ACS Secretariat as required | CONSULTED ACCOUNTABLE | LEAD RESPONSIBLE
21 | Provide Level 1 help desk with coordination of user support activities | LEAD RESPONSIBLE | SUPPORT
22 | Provide Level 2 help desk. | SUPPORT | LEAD RESPONSIBLE
23 | Provide Level 3 help desk. | SUPPORT | LEAD RESPONSIBLE
24 | Respond to escalated trouble ticket items in accordance with established procedures. | SUPPORT | LEAD RESPONSIBLE
25 | Conduct post-implementation acceptance tests and provide results. | SUPPORT | LEAD RESPONSIBLE
26 | Recommend and document process and procedures associated with change requests. | SUPPORT ACCOUNTABLE | LEAD RESPONSIBLE
27 | Perform Phase Closeout including system tuning activities, assessment of knowledge transfer tasks, transfer project artifacts to project repository, lessons learned document, update Business Solution, and transition support to ACS ICT Operations | SUPPORT ACCOUNTABLE | LEAD RESPONSIBLE
28 | Provide processes and procedures for tracking and reporting the status of all warranty services. | SUPPORT ACCOUNTABLE | LEAD RESPONSIBLE

## Data (hidden)
Compliance
NOT AVAILABLE
YES
NO
TO BE CONFIRMED